## ProcessCharter
Business Process Mapping & Optimization – Process Charter
Process Name | Owner | Stakeholders | Scope | Objectives | Current Challenges
Order-to-Cash | Operations Manager | Sales, Finance, Warehouse, Logistics | From customer order placement to payment receipt | Reduce processing time, minimize errors, improve cash flow | Manual approvals, duplicate data entry, delayed invoicing

## ProcessKPIs
Process KPIs – As-Is vs To-Be Comparison
KPI | As-Is Value | To-Be Target | % Improvement | Formula
Cycle Time (hrs) | 72 | 24 | -66.67% | % improvement = (To-Be - As-Is)/As-Is
Error Rate (%) | 10% | 2% | -80% | Error Rate = Errors / Total Transactions
Cost per Transaction (₹) | 1200 | 800 | -33.33% | Cost = Total Process Cost / Volume
Customer Satisfaction | 3.2 | 4.5 | 40.62% | CSAT Score (1-5 scale)
First Pass Yield (%) | 72% | 95% | 31.94% | FPY = Correct First Time / Total
Manual Touch Points | 12 | 4 | -66.67% | Count of manual steps in process

## GapAnalysis
Gap Analysis – Bottlenecks & Issues
Step # | Process Step | Issue / Bottleneck | Impact (H/M/L) | Optimization Proposal
1 | Customer Places Order | Manual entry into two separate systems | H | Integrate CRM and ERP for single data entry
2 | Warehouse Packing | No real-time inventory visibility | H | Implement barcode-based WMS
3 | Courier Pickup | Pickup schedule manually tracked in spreadsheet | M | Auto-schedule via logistics API
4 | Invoice Generation | Manual PDF creation and email | H | RPA to auto-generate and send invoices
5 | Payment Reconciliation | Mismatch errors in bank reconciliation | M | Auto-match using ERP bank module
6 | Manager Approval | Single-point approval bottleneck | H | Delegation rules + escalation workflow

## ImplementationRoadmap
Implementation Roadmap – Process Optimization
Phase | Activity | Owner | Start Week | End Week | Status
Phase 1 | As-Is Process Mapping | Business Analyst | 1 | 2 | Completed
Phase 1 | KPI Baseline Collection | Operations | 1 | 2 | Completed
Phase 2 | Gap Analysis & Report | Process Lead | 3 | 4 | In Progress
Phase 2 | To-Be Design Workshop | All Stakeholders | 3 | 4 | In Progress
Phase 3 | ERP-CRM Integration Setup | IT Team | 5 | 7 | Planned
Phase 3 | RPA Bot Development | Automation Team | 5 | 8 | Planned
Phase 4 | UAT & Pilot Run | QA + Operations | 9 | 10 | Planned
Phase 5 | Go-Live & Monitoring | Project Manager | 11 | 12 | Planned